## Cost
|  |  | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Total
Benifit |  | Advertisement | 0 | 75000 | 120000 | 150700 | 200000 | 545700
|  | Total Benefit | 0 | 75000 | 120000 | 150700 | 200000 | 545700 | 545700
COST | Development Costs | Site Development & Publishing | 20000 | 0 | 0 | 0 | 0 | 20000
|  | Server Hosting | 0 | 10000 | 10000 | 10000 | 10000 | 40000
|  | Maintenance Cost | 0 | 15000 | 15000 | 15000 | 15000 | 60000
|  | Total Development cost | 20000 | 25000 | 25000 | 25000 | 25000 | 120000 | 120000
| Operational Costs | Advertisement | 0 | 60000 | 50000 | 50000 | 40000 | 200000
|  | Management | 0 | 30000 | 40000 | 50000 | 50000 | 170000
|  | Total Operational Cost | 0 | 90000 | 90000 | 100000 | 90000 | 370000 | 370000
| Total Costs |  | 20000 | 115000 | 115000 | 125000 | 115000 | 490000 | 490000
Net Benefits = Total benefits - Total cost |  |  | [20,000] | [40,000] | 5000 | 25700 | 85000 | 55700
Cumulative Net Cash Flow |  |  | [20,000] | [60,000] | [55,000] | [29,300] | 55700
Return on Investment (ROI) |  |  | 11.36% (55,700 / 490,000)*100%
Break-even Point (BEP) |  |  | 2.3 years [2 years + (85,000 - 55,700) / 85,000]

## Time-Table
Project Time Scheduling
Purpose | Duration
Project Selection | 3rd Week
Project Propossal | 4th Week
UML Design | 5th Week
Project Update | 6th - 11th Week
Develop & Testing | 12th - 13th Week
Final Presentation & Report Writing | 14th Week